## 📋 Project Overview
SAYS (Service At Your Step) – Fresher Team Project Plan
Manager's Estimation & Recruitment Planning Dashboard ¦ VBLP Tech Solutions Pvt. Ltd
▶ PROJECT CONFIGURATION (Edit yellow cells)
Project Start Date | 2026-08-01 | YYYY-MM-DD
Total Freshers | 3 | 1 = Backend, 1 = Frontend, 1 = QA
Experienced Mentors | 2 | Senior Dev + Tech Lead
Mentor Weekday Hours/day | 0.5 | Hours per fresher per weekday
Mentor Weekend Hours/day | 1 | Hours per fresher per weekend day
Fresher Working Hrs/day | 8 | Standard work hours
Work Days per Week | 5 | Mon-Fri
Weekend Days per Week | 2 | Sat-Sun
▶ TEAM MEMBERS
Name | Role | Type | Start Date | Skills to Learn | Monthly Cost (₹)
Person1 | Backend Developer (Node.js) | Fresher | 2026-08-01 | Node.js, Express, MongoDB, REST APIs, JWT, Socket.IO
Person2 | Frontend / Flutter Developer | Fresher | 2026-08-01 | Flutter, Dart, Firebase, UI/UX, Google Maps SDK
Person3 | QA / Testing Engineer | Fresher | 2026-08-01 | Manual Testing, Postman, Jest, Appium, Accessibility
Experiened person1 | Tech Lead / Senior Dev | Experienced | 2026-08-01 | All stack – Mentoring & Architecture review
Experiened person2 | Senior Backend Engineer | Experienced | 2026-08-01 | Node.js, AWS, DevOps, AI IVR – Code reviews
▶ COLOUR LEGEND
Editable Input Cell
Fresher Team Member
Experienced Mentor
Risk / Issue
Completed / On-track

## 📚 Learning Plan
SAYS Project – Technology Learning Plan (Weeks 1–8)
Freshers must complete learning tracks BEFORE or PARALLEL to development. Experienced mentors guide during daily half-hour (weekday) / 1-hour (weekend) sessions.
Week | Phase | Technology / Topic | Assigned To | Learning Hours | Resources / Tools | Key Outcome | Mentor Session? | Complexity | Priority
1 | Pre-Dev | Git & Version Control | All 3 Freshers | 8 | GitHub Docs, freeCodeCamp | Repo setup, branching, PRs | Yes | Low | 🔴 Critical
1 | Pre-Dev | VS Code & Dev Environment Setup | All 3 Freshers | 4 | Official docs | IDE ready, extensions installed | Yes | Low | 🔴 Critical
1 | Pre-Dev | REST API Concepts | Person1 (Backend) | 8 | Postman Learning Center | Understand GET/POST/PUT/DELETE | Yes | Low | 🔴 Critical
1 | Pre-Dev | Flutter Installation & Dart Basics | Priya (Frontend) | 8 | Flutter.dev | App runs on emulator | Yes | Low | 🔴 Critical
1 | Pre-Dev | Software Testing Fundamentals | Arjun (QA) | 8 | ISTQB Foundation free course | Test case writing | Yes | Low | 🔴 Critical
2 | Pre-Dev | Node.js Fundamentals | Person1 (Backend) | 16 | Node.js official docs, Traversy Media | Build simple HTTP server | Yes | Medium | 🔴 Critical
2 | Pre-Dev | Express.js Framework | Person1 (Backend) | 12 | Express.js docs | Create REST endpoints | Yes | Medium | 🔴 Critical
2 | Pre-Dev | Dart Language Deep Dive | Priya (Frontend) | 16 | Dart.dev tours | OOP in Dart, null safety | Yes | Medium | 🔴 Critical
2 | Pre-Dev | Flutter Widgets & Layouts | Priya (Frontend) | 12 | Flutter cookbook | Build basic screens | Yes | Medium | 🔴 Critical
2 | Pre-Dev | Postman API Testing | Arjun (QA) | 16 | Postman Academy | Test existing APIs | Yes | Low | 🟠 High
3 | Pre-Dev | MongoDB Basics | Ravi (Backend) | 16 | MongoDB University M001 | CRUD operations | Yes | Medium | 🔴 Critical
3 | Pre-Dev | Mongoose ODM | Ravi (Backend) | 10 | Mongoose docs | Schema modeling | Yes | Medium | 🔴 Critical
3 | Pre-Dev | Flutter Navigation & State | Priya (Frontend) | 16 | Flutter docs – Navigation | Multi-screen app | Yes | Medium | 🔴 Critical
3 | Pre-Dev | Firebase Integration (Flutter) | Priya (Frontend) | 10 | Firebase codelab | Auth & Firestore basics | Yes | Medium | 🟠 High
3 | Pre-Dev | Test Case Design Techniques | Arjun (QA) | 16 | ISTQB, YouTube | BVA, EP, decision tables | Yes | Low | 🟠 High
4 | Pre-Dev | JWT Authentication | Ravi (Backend) | 10 | Auth0 blog, YouTube | Secure login endpoint | Yes | Medium | 🔴 Critical
4 | Pre-Dev | Firebase Auth & OTP | Ravi (Backend) | 8 | Firebase docs | OTP login working | Yes | Medium | 🔴 Critical
4 | Pre-Dev | Flutter Forms & Validation | Priya (Frontend) | 12 | Flutter docs | Login/Register form | Yes | Medium | 🔴 Critical
4 | Pre-Dev | Google Maps SDK (Flutter) | Priya (Frontend) | 10 | Google Maps Flutter plugin | Map renders in app | Yes | High | 🟠 High
4 | Pre-Dev | Mobile Testing & Appium Intro | Arjun (QA) | 16 | Appium docs, YouTube | Setup Appium env | Yes | High | 🟡 Medium
5 | Dev Phase | Socket.IO Real-Time | Ravi (Backend) | 12 | Socket.IO docs | Live tracking events | Yes | High | 🔴 Critical
5 | Dev Phase | Stripe Payment Integration | Ravi (Backend) | 10 | Stripe docs | Test payment flow | Yes | High | 🔴 Critical
5 | Dev Phase | Flutter Provider / Riverpod | Priya (Frontend) | 14 | riverpod.dev | State management | Yes | High | 🟠 High
5 | Dev Phase | Flutter – Real-time Socket client | Priya (Frontend) | 10 | socket_io_client pub.dev | Live GPS map update | Yes | High | 🔴 Critical
5 | Dev Phase | API Automation (Jest / Supertest) | Arjun (QA) | 16 | Jest docs, Supertest GitHub | Automate booking API | Yes | Medium | 🟠 High
6 | Dev Phase | Twilio Voice & IVR | Ravi (Backend) | 14 | Twilio docs, quickstart | Receive incoming call | Yes | High | 🔴 Critical
6 | Dev Phase | OpenAI API Integration | Ravi (Backend) | 12 | OpenAI API docs | AI responds to prompts | Yes | High | 🔴 Critical
6 | Dev Phase | Flutter Notifications (FCM) | Priya (Frontend) | 10 | Firebase Cloud Messaging | Push notification received | Yes | Medium | 🟠 High
6 | Dev Phase | Flutter Accessibility (Elder UI) | Priya (Frontend) | 12 | Flutter a11y docs | Large text, contrast pass | Yes | Medium | 🔴 Critical
6 | Dev Phase | Performance & Load Testing | Arjun (QA) | 14 | k6 / JMeter free | 1000 user load test | Yes | High | 🟡 Medium
7 | Dev Phase | AWS EC2 & Deployment Basics | Ravi (Backend) | 10 | AWS Free Tier, tutorials | Backend live on EC2 | Yes | High | 🟠 High
7 | Dev Phase | Docker Fundamentals | Ravi (Backend) | 8 | Docker Docs | Containerise Node app | Yes | High | 🟡 Medium
7 | Dev Phase | Flutter Build & Play Store Prep | Priya (Frontend) | 10 | Flutter deployment guide | APK / AAB generated | Yes | Medium | 🟠 High
7 | Dev Phase | Security Testing Basics | Arjun (QA) | 12 | OWASP Top 10, Burp Community | Auth vulnerability check | Yes | High | 🟠 High
7 | Dev Phase | Elder Usability Testing Methods | Arjun (QA) | 10 | Nielsen Norman Group articles | Usability test script | Yes | Low | 🔴 Critical
8 | Integration | CI/CD with GitHub Actions | All (guided) | 4 each | GitHub Actions docs | Auto deploy on push | Yes | High | 🟡 Medium
8 | Integration | End-to-End Test Rehearsal | All 3 Freshers | 8 each | Internal test plan | Full booking flow tested | Yes | Medium | 🔴 Critical
8 | Integration | AI IVR Full Workflow Test | Ravi + Arjun | 12 | Internal doc | Voice booking works | Yes | High | 🔴 Critical
TOTAL LEARNING HOURS (approx.) |  |  | 0

## 📅 Weekly Timeline
SAYS Project – 24-Week Master Development Timeline (Fresher Team with Mentoring)
Original SAYS doc estimates 3-month MVP for experienced team. With freshers + mentoring, realistic timeline is 24 weeks (6 months).
Week | Phase | Main Activities | Ravi – Backend Tasks | Priya – Frontend Tasks | Arjun – QA Tasks | Mentor Focus | Fresher Hrs | Mentor Hrs | Cumul. Hrs | Status | Key Deliverable | Risk
1 | 🎓 Learning | Git, Dev setup, REST intro | Git + Node.js env setup | Flutter install + Dart basics | Testing fundamentals | Git workflow, project structure | 120 | 15 | 120 | ⬜ Planned | Dev environments ready | Low
2 | 🎓 Learning | Core backend & frontend frameworks | Node.js + Express basics | Dart OOP + Flutter widgets | Postman API exploration | Code review first Node API | 120 | 15 | 240 | ⬜ Planned | Basic screens + API endpoints | Low
3 | 🎓 Learning | Database + state management | MongoDB CRUD + Mongoose | Flutter Navigation + Firebase | Test case design | DB schema review | 120 | 15 | 360 | ⬜ Planned | DB connected; multi-screen app | Medium
4 | 🎓 Learning | Auth + maps + mobile testing | JWT + Firebase OTP | Google Maps Flutter | Appium setup | Auth flow review | 120 | 15 | 480 | ⬜ Planned | Login/OTP working end-to-end | Medium
5 | 🎓 Learning | Real-time + payments + auto testing | Socket.IO + Stripe | Provider/Riverpod + Socket client | Jest API automation | Architecture design session | 120 | 15 | 600 | ⬜ Planned | Payment flow + live tracking | High
6 | 🎓 Learning | AI IVR + notifications + perf testing | Twilio + OpenAI APIs | FCM + Elder-friendly UI | Load testing with k6 | AI call workflow walkthrough | 120 | 15 | 720 | ⬜ Planned | AI IVR receives call + responds | High
7 | 🎓 Learning | Deployment + security | AWS EC2 + Docker | App build + Play Store prep | Security testing (OWASP) | Deployment strategy review | 120 | 15 | 840 | ⬜ Planned | Backend live on EC2 | High
8 | 🎓 Learning | CI/CD + end-to-end rehearsal | GitHub Actions setup | Flutter CI integration | E2E test scenarios | Full system walkthrough | 120 | 15 | 960 | ⬜ Planned | CI/CD pipeline green | Medium
9 | 🔨 Dev | User Auth System | POST /register /login /verify-otp | Login + Registration screens | Auth API test suite | Code review auth module | 120 | 18 | 1080 | ⬜ Planned | Working OTP login | Medium
10 | 🔨 Dev | Booking System Backend | POST /book-service, booking DB | Service category listing UI | Booking flow test cases | Booking logic review | 120 | 18 | 1200 | ⬜ Planned | End-to-end booking created | High
11 | 🔨 Dev | Provider Management APIs | GET /available-providers, matching algo | Provider profile screens | Provider API tests | Provider matching algorithm | 120 | 18 | 1320 | ⬜ Planned | Auto-assign provider logic | High
12 | 🔨 Dev | GPS Tracking + Real-time | Socket.IO tracking events | Google Maps live tracking | Real-time tracking tests | Performance of Socket.IO | 120 | 18 | 1440 | ⬜ Planned | Provider location on map | High
13 | 🔨 Dev | Payment Integration | Stripe /create-payment /verify | Payment screens + receipt UI | Payment flow tests | Stripe test mode review | 120 | 18 | 1560 | ⬜ Planned | Test payment successful | High
14 | 🔨 Dev | AI IVR System | Twilio + OpenAI + call routing | Voice booking indicator UI | IVR call flow tests | AI conversation tuning | 120 | 18 | 1680 | ⬜ Planned | Voice call books a service | Very High
15 | 🔨 Dev | Notifications + Admin Dashboard | Firebase push + SMS Twilio | Notification UI + Admin web views | Notification delivery tests | Admin dash review | 120 | 18 | 1800 | ⬜ Planned | Admin can manage bookings | Medium
16 | 🔨 Dev | Elder-Friendly UI Polish | – | Large fonts, contrast, big buttons | Accessibility audit (WCAG) | Accessibility review session | 120 | 18 | 1920 | ⬜ Planned | WCAG AA pass | High
17 | 🧪 Testing | System Integration Testing | Fix backend bugs | Fix UI bugs | Full regression suite | Daily 45-min bug triage | 120 | 20 | 2040 | ⬜ Planned | Stable integrated build | Medium
18 | 🧪 Testing | Elder Usability Testing | Backend fixes | UI adjustments from sessions | Run usability sessions | Observe + guide sessions | 120 | 20 | 2160 | ⬜ Planned | 5 elder users tested | High
19 | 🧪 Testing | Security & Performance Testing | Security fixes | – | Security + load test results | Security review | 120 | 20 | 2280 | ⬜ Planned | No critical vulnerabilities | High
20 | 🚀 Deploy | AWS Deployment + MongoDB Atlas | Deploy EC2 + Atlas setup | – | Smoke test on production | Deployment supervision | 120 | 20 | 2400 | ⬜ Planned | Production env live | Very High
21 | 🚀 Deploy | App Store Preparation | – | Build APK/AAB + store listing | App store smoke tests | Play Store review guidance | 120 | 20 | 2520 | ⬜ Planned | Apps submitted to stores | High
22 | 🚀 Deploy | CI/CD + Docker Finalise | GitHub Actions + Docker | – | Pipeline test | CI/CD architecture review | 120 | 20 | 2640 | ⬜ Planned | Auto-deploy on merge | Medium
23 | 🚀 Deploy | Soft Launch + Bug Fix | Monitor backend logs | Monitor app | Production monitoring | Daily check-in | 120 | 20 | 2760 | ⬜ Planned | Live MVP with 50 users | Very High
24 | 🚀 Deploy | Launch Stabilisation | Performance tuning | UI final tweaks | Production test suite | Sign-off review | 120 | 20 | 2880 | ⬜ Planned | Full MVP accepted | High
TOTALS | [6 empty] | 2880 | 424

## ⏱ Hours & Cost
SAYS – Weekly Hours Logged & Cost Estimation
Track actual hours each week. Edit orange cells for actuals. All cost cells auto-calculate.
HOURLY RATE ASSUMPTIONS (Edit yellow)
Ravi – Backend (Fresher) |  | per hour (editable)
Priya – Frontend (Fresher) |  | per hour (editable)
Arjun – QA (Fresher) |  | per hour (editable)
Sneha – Tech Lead (Exp.) |  | per hour (editable)
Vikram – Sr. Backend (Exp.) |  | per hour (editable)
Week | Phase | Ravi Hrs (Planned) | Ravi Hrs (Actual) | Priya Hrs (Planned) | Priya Hrs (Actual) | Arjun Hrs (Planned) | Arjun Hrs (Actual) | Mentor Hrs (Total) | Total Fresher Hrs | Est. Cost (₹)
1 | 🎓 Learning | 40 |  | 40 |  | 40 |  | 15 | 120 | 21855
2 | 🎓 Learning | 40 |  | 40 |  | 40 |  | 15 | 120 | 21855
3 | 🎓 Learning | 40 |  | 40 |  | 40 |  | 15 | 120 | 21855
4 | 🎓 Learning | 40 |  | 40 |  | 40 |  | 15 | 120 | 21855
5 | 🎓 Learning | 40 |  | 40 |  | 40 |  | 15 | 120 | 21855
6 | 🎓 Learning | 40 |  | 40 |  | 40 |  | 15 | 120 | 21855
7 | 🎓 Learning | 40 |  | 40 |  | 40 |  | 15 | 120 | 21855
8 | 🎓 Learning | 40 |  | 40 |  | 40 |  | 15 | 120 | 21855
9 | 🔨 Dev | 40 |  | 40 |  | 40 |  | 18 | 120 | 23226
10 | 🔨 Dev | 40 |  | 40 |  | 40 |  | 18 | 120 | 23226
11 | 🔨 Dev | 40 |  | 40 |  | 40 |  | 18 | 120 | 23226
12 | 🔨 Dev | 40 |  | 40 |  | 40 |  | 18 | 120 | 23226
13 | 🔨 Dev | 40 |  | 40 |  | 40 |  | 18 | 120 | 23226
14 | 🔨 Dev | 40 |  | 40 |  | 40 |  | 18 | 120 | 23226
15 | 🔨 Dev | 40 |  | 40 |  | 40 |  | 18 | 120 | 23226
16 | 🔨 Dev | 40 |  | 40 |  | 40 |  | 18 | 120 | 23226
17 | 🧪 Testing | 40 |  | 40 |  | 40 |  | 20 | 120 | 24140
18 | 🧪 Testing | 40 |  | 40 |  | 40 |  | 20 | 120 | 24140
19 | 🧪 Testing | 40 |  | 40 |  | 40 |  | 20 | 120 | 24140
20 | 🚀 Deploy | 40 |  | 40 |  | 40 |  | 20 | 120 | 24140
21 | 🚀 Deploy | 40 |  | 40 |  | 40 |  | 20 | 120 | 24140
22 | 🚀 Deploy | 40 |  | 40 |  | 40 |  | 20 | 120 | 24140
23 | 🚀 Deploy | 40 |  | 40 |  | 40 |  | 20 | 120 | 24140
24 | 🚀 Deploy | 40 |  | 40 |  | 40 |  | 20 | 120 | 24140
GRAND TOTAL |  | 960 |  | 960 |  | 960 |  | 424 | 2880 | 553768

## ⚠️ Risk Register
SAYS – Risk Register
| Risk Description | Probability (1-5) | Impact (1-5) | Risk Score | Mitigation Strategy | Owner | Week Identified | Status
Freshers take longer to learn Node.js / Flutter than planned | Freshers take longer to learn Node.js / Flutter than planned | 4 | 4 | 16 | Weekly assessment tests; 2-week buffer in learning phase | Tech Lead | 1 | 🟡 Monitor
AI IVR integration (Twilio + OpenAI) too complex for freshers | AI IVR integration (Twilio + OpenAI) too complex for freshers | 4 | 5 | 20 | Experienced mentor leads AI module; fresher assists only | Tech Lead | 6 | 🔴 High
Elder usability testing not organised in time | Elder usability testing not organised in time | 3 | 4 | 12 | Recruit 10 elder test users by Week 10 | Project Manager | 8 | 🟡 Monitor
Scope creep (client adds features mid-development) | Scope creep (client adds features mid-development) | 3 | 5 | 15 | Strict MVP boundary; change control process | Project Manager | 1 | 🟡 Monitor
AWS / Cloud costs exceed budget | AWS / Cloud costs exceed budget | 2 | 3 | 6 | Use AWS Free Tier in dev; budget alert at 80% | DevOps Engineer | 9 | ⬜ Low
Mentor not available for daily sessions | Mentor not available for daily sessions | 3 | 4 | 12 | Async code review via GitHub; recorded sessions | Tech Lead | 1 | 🟡 Monitor
Security vulnerabilities (auth / payment) | Security vulnerabilities (auth / payment) | 2 | 5 | 10 | OWASP checklist; Stripe test mode; JWT refresh tokens | QA + Backend | 17 | 🟡 Monitor
App Store rejection (Play Store / App Store) | App Store rejection (Play Store / App Store) | 2 | 3 | 6 | Follow store guidelines from Week 7; test AAB format | Flutter Dev | 21 | ⬜ Low
Performance issues at scale (Socket.IO) | Performance issues at scale (Socket.IO) | 3 | 4 | 12 | Load test with k6 in Week 19; Redis for socket scaling | Backend Dev | 12 | 🟡 Monitor
Fresher burnout due to steep learning curve | Fresher burnout due to steep learning curve | 3 | 4 | 12 | Regular 1:1 check-ins; pair programming sessions | Project Manager | 1 | 🟡 Monitor

## 🗓 Training Calendar
SAYS – 8-Week Technology Training Calendar (Fresher-wise)
Each cell shows the topic being studied that week. 🔵 = Ravi (Backend) 🟠 = Priya (Frontend) 🟢 = Arjun (QA) All = Everyone
Week | Mon–Tue | Wed | Thu | Fri | Sat (Weekend) | Sun (Weekend) | Mentor Session
1 | All: Git + Dev Setup | All: REST intro | 🔵 Node.js basics 🟠 Dart basics 🟢 Test fundaments | 🔵 Node.js basics 🟠 Dart basics 🟢 Test fundaments | 🔵 Express intro 🟠 Flutter setup 🟢 Postman | 🔵 Express CRUD 🟠 Flutter widgets 🟢 Test cases | Mentor: Project structure, coding standards
2 | 🔵 Node.js deep 🟠 Flutter layout 🟢 Postman API | 🔵 Node.js async 🟠 Flutter forms 🟢 API exploration | 🔵 Express Router 🟠 Flutter state 🟢 Equivalence part | 🔵 Express Router 🟠 Flutter state 🟢 Boundary testing | 🔵 MongoDB intro 🟠 Dart OOP 🟢 Test case writing | 🔵 MongoDB CRUD 🟠 Flutter Nav 🟢 Bug reporting | Mentor: Review first API + first screen
3 | 🔵 Mongoose ODM 🟠 Firebase Auth 🟢 Test design | 🔵 Mongoose ODM 🟠 Firebase Firestore 🟢 Test design | 🔵 Schema design 🟠 Flutter Nav deep 🟢 Test execution | 🔵 Schema relations 🟠 State management 🟢 Defect mgmt | 🔵 Aggregation 🟠 Firebase OTP 🟢 Appium intro | 🔵 Index + query opt 🟠 Flutter advanced 🟢 Appium setup | Mentor: DB schema review + test plan review
4 | 🔵 JWT Auth 🟠 Google Maps 🟢 Appium scripting | 🔵 JWT middleware 🟠 Maps markers 🟢 Mobile test cases | 🔵 Firebase OTP 🟠 Location perms 🟢 Mobile automation | 🔵 Role management 🟠 Maps + tracking 🟢 CI test basics | 🔵 Session handling 🟠 Map customise 🟢 Test reporting | 🔵 Auth testing 🟠 UX polish 🟢 Regression suite | Mentor: Auth flow end-to-end demo
5 | 🔵 Socket.IO 🟠 Provider/Riverpod 🟢 Jest intro | 🔵 Socket events 🟠 Socket client Flutter 🟢 Jest API tests | 🔵 Stripe integration 🟠 Payment UI 🟢 Payment test cases | 🔵 Stripe webhooks 🟠 Booking flow UI 🟢 End-to-end tests | 🔵 Stripe testing 🟠 Booking history 🟢 Load test intro (k6) | 🔵 Real-time review 🟠 UI consistency 🟢 k6 script writing | Mentor: Payment + real-time architecture
6 | 🔵 Twilio setup 🟠 FCM notifications 🟢 Load testing | 🔵 IVR call flow 🟠 Notification UI 🟢 Performance report | 🔵 OpenAI API 🟠 Elder UI: fonts 🟢 Security (OWASP) | 🔵 AI prompts 🟠 Elder UI: contrast 🟢 Security checklist | 🔵 AI IVR test calls 🟠 Elder: big buttons 🟢 Accessibility test | 🔵 Call routing 🟠 Voice UX 🟢 WCAG audit | Mentor: AI IVR architecture deep-dive
7 | 🔵 AWS EC2 setup 🟠 Flutter build APK 🟢 Sec testing | 🔵 Docker intro 🟠 App store prep 🟢 Vuln reporting | 🔵 Docker Node.js 🟠 Store listing 🟢 Pen test basics | 🔵 Env config 🟠 Screenshots 🟢 Security fixes | 🔵 Nginx basics 🟠 App build test 🟢 Regression run | 🔵 MongoDB Atlas 🟠 iOS build 🟢 QA sign-off | Mentor: Deployment walkthrough + store submission
8 | All: GitHub Actions CI/CD setup | All: Docker compose Multi-container | 🔵 E2E backend test 🟠 E2E UI test 🟢 Full regression | 🔵 AI IVR E2E 🟠 Track E2E 🟢 IVR test cases | All: Bug fixing from E2E | All: Sprint review Demo prep | Mentor: Full system review + go/no-go for Dev phase